## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
TRUE
Data Analysis Mastery
Dev10 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  | Med risk | High risk | Unassigned
Darrell Gerber
Project Start Date: | 2021-12-15 |  |  |  |  | December
Scrolling Increment: | 0 |  |  |  |  | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T
Project Management Plan
Start PMP | On Track | Name | 100% | 2021-12-15 | 1
Submit for Review | Milestone |  |  | 2021-12-15 | 1 | 1
Update based on Review |  |  | 100% | 2021-12-16 | 1
ETL |  |  |  | 2021-12-16
Create ERD |  |  | 0% | 2021-12-16 | 1
Clean Data |  |  | 100% | 2021-12-16 | 1
Write ETL Report |  |  | 0% | 2021-12-16 | 1
Submit for Review | Milestone |  |  | 2021-12-17 | 1 |  |  | 1
Update based on Review |  |  | 0% | 2021-12-18 | 1
Dashboard
Napkin 1 |  |  |  | 2021-12-14 | 1
Feedback |  |  |  | 2021-12-15 | 1
Update Napkin |  |  |  | 2021-12-15 | 1
Document |  |  |  | 2021-12-15 | 1
Dashboard Data Transforms |  |  |  | 2021-12-15 | 1
Build Dashboard |  |  |  | 2021-12-15 | 2
Submit for Review | Milestone |  |  | 2021-12-17 | 1 |  |  | 1
Update based on Review |  |  |  | 2021-12-18 | 1
Report
Determine and Document Factors of Life |  |  |  | 2021-12-14 | 1
Introduce and Cite Datasets |  |  |  | 2021-12-14 | 1
Describe discovery |  |  |  | 2021-12-15 | 2
Visualizations (1/2 Power BI, 1/2 Excel) |  |  |  | 2021-12-15 | 2
Explain visualizations |  |  |  | 2021-12-15 | 2
Analysis Toolpak elements |  |  |  | 2021-12-15 | 1
Decisions and Recommendations based on analysis |  |  |  | 2021-12-16 | 1
First Draft | Milestone |  |  | 2021-12-16 | 1 |  | 1
Revisions |  |  |  | 2021-12-17 | 1
Final Submission
Check punchlist | Goal |  |  | 2021-12-17 | 1 |  |  | 2
Submit | Milestone |  |  | 2021-12-17 | 1 |  |  | 1
To add more data, Insert new rows ABOVE this one